## Sheet1
Log Number | Team Member | Date | Hours | Minutes | Description
1 | Aiden Patel | 2024-09-23 | 0 | 15 | create forked repo for project 2 and set 'project-2' as default branch. Hopefully blocked modifications to 'main' branch but I'll validate that later
2 | Aiden Patel, Andrew McFerrin, John Newman, Kai Achen, Landon Pyko | 2024-09-23 | 1 | 10 | scan through code to understand. make list of known bugs. diagram supershot. outlined tasks. create time estimate, fixed ship intersect issue
3 | Aiden Patel, Andrew, Kai, Landon | 2024-09-25 | 0 | 20 | GTA team meeting, discussed supershot and AI method and how to break up work
4 | Andrew McFerrin | 2024-09-25 | 4 | 30 | started work on ai behavior
5 | Aiden Patel | 2024-09-25 | 2 | 40 | Implemented super shot and added terminal clears so that players can't see each others' boards
6 | Andrew McFerrin | 2024-09-26 | 0 | 30 | Fixed some logic in the medium difficulty ai
7 | Aiden Patel, Andrew McFerrin | 2024-09-26 | 0 | 30 | talked through AI logic and improved some logic
8 | Kai Achen | 2024-09-26 | 0 | 40 | added board construction and shooting functions to AI class
9 | Kai Achen | 2024-09-26 | 0 | 5 | resolved some merge conflicts
10 | Landon Pyko | 2024-09-26 | 0 | 35 | Scanned through code. Helped Kai resolve conflicts. Started updating the worklog file. Planning to look at medium difficulty
11 | Andrew McFerrin | 2024-09-27 | 0 | 40 | Added all comments to ai shooting behavior code
12 | Landon Pyko, Aiden Patel, Andrew McFerrin | 2024-09-28 | 0 | 5 | Discussed ship difficulty logic
13 | Aiden Patel | 2024-09-28 | 1 | 0 | Changed AI class to inherit Player so that functions aren't being recreated. Overwrote some functions from Player and GameObject to fit the AI better. Ship placement logic may be done but hasn't been tested and isn't optimized since it's always randomizing without knowledge of previous ship placements or board boundaries and instead error checks each time. Started to modify __take_turn() to take in coordinates from aiTurn but still needs a lot of attention. Waiting for Andrew to push comments on aiTurn function before I start messing with it so that merge conflicts are avoided
14 | Aiden Patel | 2024-09-28 | 1 | 0 | Overwrote get_input in AI class to just return coordinate from aiTurn. Added gameloop logic so that you can actually play against AI now. Seems that at least easy mode is working, haven't had a chance to test other modes
15 | Aiden Patel | 2024-09-28 | 2 | 30 | Cleaned some more code and implemented medium and hard difficulty for the AI
16 | Landon Pyko | 2024-09-28 | 2 | 0 | Made better transitions between Player -> Player and Player -> AI based off of input buffer instead of waiting. Spent a lot of time stress testing with different combinations of AI difficulties, ship amounts, ship directions, and super shot. Updated worklog to be up to date.
17 | John Newman | 2024-09-29 | 0 | 56 | Intended to check that project meets requirements. It does as far as I could tell, minus documentation. Found some errors listed in general.
18 | John Newman | 2024-09-29 | 1 | 18 | Fixed some errors and changed some display code.
19 | John Newman | 2024-09-29 | 1 | 28 | made documentation pdf, contains information on all py files in project
|  | Total Time | Hours | Minutes
| Aiden Patel |  | 9 | 30
| Andrew McFerrin |  | 7 | 25
| John Newman |  | 4 | 52
| Kai Achen |  | 1 | 55
| Landon Pyko |  | 3 | 50
|  |  | 27 | 32