## Sheet1
Log Number | Team Member | Date | Hours | Minutes | Description
1 | Aiden Patel | 2024-09-23 | 0 | 15 | create forked repo for project 2 and set 'project-2' as default branch. Hopefully blocked modifications to 'main' branch but I'll validate that later
2 | Team | 2024-09-23 | 1 | 10 | scan through code to understand. make list of known bugs. diagram supershot. outlined tasks. create time estimate, fixed ship intersect issue
3 | Aiden, Andrew, Kai, Landon | 2024-09-25 | 0 | 20 | GTA team meeting, discussed supershot and AI method and how to break up work
4 | Andrew | 2024-09-25 | 4 | 30 | started work on ai behavior
5 | Aiden | 2024-09-25 | 2 | 40 | Implemented super shot and added terminal clears so that players can't see each others' boards
6 | Andrew | 2024-09-26 | 0 | 30 | Fixed some logic in the medium difficulty ai
7 | Aiden and Andrew | 2024-09-26 | 0 | 30 | talked through AI logic and improved some logic
8 | Kai | 2024-09-26 | 0 | 40 | added board construction and shooting functions to AI class
9 | Kai | 2024-09-26 | 0 | 5 | resolved some merge conflicts
10 | Landon | 2024-09-26 | 0 | 35 | Scanned through code. Helped Kai resolve conflicts. Started updating the worklog file. Planning to look at medium difficulty