## Sheet1
Log Number | Team Member | Date | Hours | Minutes | Description
1 | Aiden Patel | 2024-09-23 | 0 | 15 | create forked repo for project 2 and set 'project-2' as default branch. Hopefully blocked modifications to 'main' branch but I'll validate that later
2 | Team | 2024-09-23 | 1 | 10 | scan through code to understand. make list of known bugs. diagram supershot. outlined tasks. create time estimate, fixed ship intersect issue
3 | Aiden, Andrew, Kai, Landon | 2024-09-25 | 0 | 20 | GTA team meeting, discussed supershot and AI method and how to break up work
4 | Andrew | 2024-09-25 | 4 | 30 | started work on ai behavior
5 | Aiden | 2024-09-25 | 2 | 40 | Implemented super shot and added terminal clears so that players can't see each others' boards
6 | Andrew | 2024-09-26 | 0 | 30 | Fixed some logic in the medium difficulty ai
7 | Aiden and Andrew | 2024-09-26 | 0 | 30 | talked through AI logic and improved some logic
8 | Kai | 2024-09-26 | 0 | 40 | added board construction and shooting functions to AI class
9 | Kai | 2024-09-26 | 0 | 5 | resolved some merge conflicts
10 | Landon | 2024-09-26 | 0 | 35 | Scanned through code. Helped Kai resolve conflicts. Started updating the worklog file. Planning to look at medium difficulty
11 | Andrew | 2024-09-27 | 0 | 40 | Added all comments to ai shooting behavior code
12 | Landon, Aiden, Andrew | 2024-09-28 | 0 | 5 | Discussed ship difficulty logic
13 | Aiden | 2024-09-28 | 1 | 0 | Changed AI class to inherit Player so that functions aren't being recreated. Overwrote some functions from Player and GameObject to fit the AI better. Ship placement logic may be done but hasn't been tested and isn't optimized since it's always randomizing without knowledge of previous ship placements or board boundaries and instead error checks each time. Started to modify __take_turn() to take in coordinates from aiTurn but still needs a lot of attention. Waiting for Andrew to push comments on aiTurn function before I start messing with it so that merge conflicts are avoided
14 | Aiden | 2024-09-28 | 1 | 0 | Overwrote get_input in AI class to just return coordinate from aiTurn. Added gameloop logic so that you can actually play against AI now. Seems that at least easy mode is working, haven't had a chance to test other modes
15 | Aiden | 2024-09-28 | 2 | 30 | Cleaned some more code and implemented medium and hard difficulty for the AI
16 | Landon | 2024-09-28 | 2 | 0 | Made better transitions between Player -> Player and Player -> AI based off of input buffer instead of waiting. Spent a lot of time stress testing with different combinations of AI difficulties, ship amounts, ship directions, and super shot. Updated worklog to be up to date.